## Snapshot of Expected and Actual
As of April 17
| Group Life Skills | Individual Academic or Educational Supports | Individual Behavioral and Mental Health Supports | Screening and Assessment and Care Coordination and Family Stabilization | Group Academics
Expected | 364 | 260 | 909 | 7228.94 | 888
Actual | 180 | 25 | 240 | 1653 | 881
% Complete | 49.45% | 9.615% | 26.4% | 22.87% | 99.21%
As of April 29
| Group Life Skills | Individual Academic or Educational Supports | Individual Behavioral and Mental Health Supports | Screening and Assessment and Care Coordination and Family Stabilization | Group Academics
Expected | 364 | 260 | 909 | 7228.94 | 888
Actual | 266.5 | 36.5 | 258.25 | 1696 | 663.3
% Complete | 73.21% | 14.04% | 28.41% | 23.46% | 74.7%
| Group Life Skills | Individual Academic or Educational Supports | Individual Behavioral and Mental Health Supports | Screening and Assessment and Care Coordination and Family Stabilization | Group Academics | Total Hours
2024-02-23 | 0 | 5 | 77 | 492 |  | 574
2024-03-06 | 0 | 5 | 111 | 513 | 676 | 1305
2024-04-04 | 36 | 32 | 221 | 1255 | 572 | 2116
2024-04-17 | 180 | 25 | 240 | 1653 | 881 | 2979
2024-04-29 | 266.5 | 36.5 | 258.25 | 1696 | 663.3 | 2920.55
2024-05-07 | 396 | 84 | 276.25 | 2110.25 | 702.55 | 3569.05
2024-09-30 | 364 | 260 | 909 | 7228.94 | 888 | 9649.94
% Complete | 108.8% | 32.31% | 30.39% | 29.19% | 79.12% | 36.99%
| 2024-02-23 | 2024-04-29 | 2024-09-30 | % Complete
Group Life Skills | 0 | 266.5 | 364 | 73.21%
Individual Academic or Educational Supports | 5 | 36.5 | 260 | 14.04%
Individual Behavioral and Mental Health Supports | 77 | 258.25 | 909 | 28.41%
Screening and Assessment and Care Coordination and Family Stabilization | 492 | 1696 | 7228.94 | 23.46%
Group Academics |  | 663.3 | 888 | 74.7%

## Summary Data, by Person
Date | Name | Group Life Skills Support Expected | Group Life Skills Support Actual | Individual Academic or Educational Supports Expected | Individual Academic or Educational Supports Actual | Individual Behavioral and Mental Health Supports Expected | Individual Behavioral and Mental Health Supports Actual | Screening and Assessment and Care Coordination and Family Stabilization Funding Expected | Screening and Assessment and Care Coordination and Family Stabilization Funding Actual | Group Academics Expected | Group Academics Actual
2024-04-04 | Staff 1 | 0 | 0 | 0 | 4 | 0 | 0 | 480 | 177 | 0 | 0
2024-04-04 | Staff 2 | 0 | 0 | 156 | 27 | 0 | 0 | 858 | 103 | 0 | 163
2024-04-04 | Staff 3 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 56 | 0 | 0
2024-04-04 | Staff 4 | 0 | 0 | 0 | 0 | 260 | 100 | 669 | 218 | 0 | 0
2024-04-04 | Staff 5 | 52 | 0 | 0 | 1 | 0 | 0 | 26 | 22 | 260 | 114
2024-04-04 | Staff 6 | 52 | 0 | 0 | 0 | 0 | 0 | 520 | 212 | 260 | 103
2024-04-04 | Staff 7 | 156 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 104 | 193
2024-04-04 | Staff 8 | 104 | 26 | 0 | 0 | 624 | 121 | 0 | 2 | 0 | 0
2024-04-04 | Staff 9 | 52 | 0 | 0 | 0 | 0 | 0 | 480 | 43 | 0 | 0
2024-04-04 | Staff 10 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 12 | 0 | 0
2024-04-04 | Staff 11 | 52 | 10 | 0 | 0 | 0 | 0 | 1118 | 411 | 624 | 0
2024-04-04 | TOTAL | 468 | 36 | 156 | 32 | 884 | 221 | 5697 | 1255 | 1248 | 572
2024-02-13 | Staff 1 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 39 | 0 | 0
2024-02-13 | Staff 2 | 0 | 0 | 156 | 1 | 0 | 0 | 858 | 3 | 0 | 10
2024-02-13 | Staff 3 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 48
2024-02-13 | Staff 4 | 0 | 0 | 0 | 0 | 260 | 5 | 669 | 58 | 0 | 0
2024-02-13 | Staff 5 | 52 | 0 | 0 | 3 | 0 | 0 | 26 | 14 | 260 | 0
2024-02-13 | Staff 6 | 52 | 0 | 0 | 0 | 0 | 0 | 520 | 133 | 260 | 0
2024-02-13 | Staff 7 | 156 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 104 | 0
2024-02-13 | Staff 8 | 104 | 0 | 0 | 0 | 624 | 48 |  | 2 | 0 | 0
2024-02-13 | Staff 9 | 52 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0
2024-02-13 | Staff 10 |  | 0 | 0 | 0 | 0 | 0 | 480 | 8 | 0 | 0
2024-02-13 | Staff 11 | 52 | 0 | 0 | 0 | 0 | 0 | 1118 | 92 | 624 | 0
2024-02-13 | TOTAL | 468 | 0 | 156 | 4 | 884 | 52 | 5697 | 349 | 1248 | 58
2/23/2024 Kristin Email | TOTAL | 364 | 0 | 260 | 5 | 909 | 77 | 7228 | 492 | 888
2024-03-06 | Staff 1 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 39 | 0 | 0
2024-03-06 | Staff 2 | 0 | 0 | 156 | 2 | 0 | 0 | 858 | 18 | 0 | 0
2024-03-06 | Staff 3 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 56 | 0 | 0
2024-03-06 | Staff 4 | 0 | 0 | 0 | 0 | 260 | 11 | 669 | 58 | 0 | 0
2024-03-06 | Staff 5 | 52 | 0 | 156 | 3 | 0 | 0 | 26 | 20 | 260 | 88
2024-03-06 | Staff 6 | 52 | 0 | 0 | 0 | 0 | 0 | 520 | 195 | 260 | 72
2024-03-06 | Staff 7 | 156 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 104 | 64
2024-03-06 | Staff 8 | 104 | 0 | 0 | 0 | 208 | 100 |  | 2 | 0 | 0
2024-03-06 | Staff 9 | 52 | 0 | 0 | 0 | 0 | 0 | 480 | 10 | 0 | 0
2024-03-06 | Staff 10 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 8 | 0 | 0
2024-03-06 | Staff 11 | 52 | 0 | 0 | 0 | 0 | 0 | 1118 | 107 | 52 | 0
2024-03-06 | TOTAL | 468 | 0 | 312 | 5 | 468 | 111 | 5697 | 513 | 676 | 224
2024-04-14 | Staff 1 | 0 | 0 | 0 | 0 | 0 |  | 480 | 353.25 | 0 | 0
2024-04-14 | Staff 2 | 0 | 3.5 | 156 | 24.75 | 0 |  | 858 | 336.25 | 0 | 349.45
2024-04-14 | Staff 3 | 0 | 4 | 0 | 0 | 0 |  | 78 | 283.5 | 0 | 0
2024-04-14 | Staff 4 | 289 | 0 | 0 | 0 | 260 | 191 | 669 | 633 | 0 | 0
2024-04-14 | Staff 5 | 52 | 0.25 | 0 | 0 | 0 |  | 26 | 218.75 | 260 | 251.5
2024-04-14 | Staff 6 | 52 | 3 | 0 | 0 | 0 |  | 520 | 945.75 | 260 | 175.44
2024-04-14 | Staff 7 | 156 | 23 | 0 | 0 | 0 |  | 988 | 0 | 104 | 233.5
2024-04-14 | Staff 8 | 104 | 52 | 0 | 0 | 624 | 246.5 |  | 493.25 | 0 | 0
2024-04-14 | Staff 9 | 52 | 54.5 | 0 | 0 | 0 |  | 480 | 332.25 | 0 | 2
2024-04-14 | Staff 10 |  | 0 | 0 | 0 | 0 |  | 480 | 292 | 0 | 0
2024-04-14 | Staff 11 | 52 | 0 | 0 | 0 | 0 |  | 1118 | 635.75 | 624 | 10
2024-04-14 | TOTAL | 757 | 140.25 | 156 | 24.75 | 884 | 437.5 | 5697 | 4523.75 | 1248 | 1021.89
Note on D46: Amy Rubinson: but there are also 28 hours entered through the individual system way.

## Staffing by Population
Population | # of Families | Prinary Staff | Support Staff | Supervision
LFCA | 30 | Staff 11, Staff 10, Staff 1 | Staff 11 | Staff 1
Mental Health | 50 | Staff 8, Staff 4 | Social work interns, Staff 4 | Staff 1
Mission Northstar | 30 | Ken | NA | Staff 1
Casa V | 10 | Staff 9 | NA | Staff 1 as related to FNP
P3 | 10 | Staff 4 | Staff 4 | Staff 1 as related to FNP
His House | 15 | Staff 4 | Staff 4 | Staff 1 as related to FNP
Field Academy | 30 | Staff 6, Staff 5, Staff 2 | Staff 7 | Staff 1 as related to FNP, Staff 6 as related to programming and student intake, Staff 5 as related to field trips, Staff 13 as related to vision
Edison | 30 | Staff 3 | Staff 11 | Staff 3
Homeless community | 50 | Staff 3, Staff 12, Staff 11 | Staff 11 | Staff 12 as related to the hotline, Staff 3 as related to tuition exemptions
MDC Wolfson | 10 | Staff 11 | NA | Staff 10
Citrus/Project UP-START | 50 | Staff 3 | Staff 11 | Staff 10
First Star | 30 | Staff 4 | NA | Staff 10
The One | 20 | Staff 4 | Staff 4 | Staff 10
MDC North | 15 | Staff 8 | Social work interns | Staff 10
New student intake from website (temporary support) | 50 | Staff 1 | NA | Staff 1
Emergency requests (temporary support) | 50 | Each care coordiantor submits a request, then Staff 1 works it through the approval process with the family, care coordiantor, and contract manager | Staff 11 | Staff 1 as related to FNP, Staff 14 as related to finances and audit compliance
480
[5 empty] | LFCA | 20 | Staff 11
[5 empty] | LFCA | 5 | Staff 10
[5 empty] | LFCA | 5 | Staff 1
[5 empty] | Mental health | 40 | Staff 8
[5 empty] | Mental health | 10 | Staff 4
[5 empty] | Homeless | 20 | Staff 11
[5 empty] | Homeless | 20 | Staff 3
[5 empty] | Homeless | 10 | Staff 12

## Contracted Hours and Staff Comp
Name | TCT Title prior year | Position # | Direct Service Hrs prior year | TCT Title current year | Families for prior year | Families Reassignment for current year | Direct Service Hrs current year | # of hours to optional activities | Change between 22-23 and 23-24 | How many families--DIRECT | How many families-- SUPPORT | What's happening now? | What is the plan for next year?
Staff 11 | Grad Fellow 5 | 38431 | 390 | SC 12 | Support staff--no caseload | 10 MDC Wolfson 20 homeless community 20 LFCA students 50 Citrus/Project UP-START and Edison (support) | 1111.5 | 676 | 1397.5 | 50 | 50 | Brought to fulltime starting Feb 1 2024, many of her housing clients are in homestead--long travel time, has needed significant training to step up to this level (provided by Staff 3, Staff 10, Staff 1) | Keep her in this role and continue training her. She lives near Wolfson, so would like to keep her there and reallocate Homestead community to New Hire at Educate Tomorrow who will be staffed in Homestead area. New hire planned for summer 2024.
Staff 14 | Natl. Helper | 41964 | 183.75 | NA | Support of The One (50 students) Citrus/Project UP-START Central (50 students) First Star (30 students) | 50 Citrus/Project UP-START-Staff 3, Staff 1, and Dropped 30 First Star-KEN | [5 empty] | Left Fall 2023 | NA
Staff 15 | Natl. Helper 3 | 42223 | 1176 | Natl. Helper 3 | 40 Support of Field Academy | 40 Support of Field Academy | 980.88 | 260 | -195.12 | 0 | 40 | Data has not been entered. | Will move this staff mostly/all off of FNP for next year so she can continue to serve the Field Academy families.
Staff 16 | Natl. Helper 4 | 42544 | 242.8 | NA | Support staff--emerngecy requests, and new student intake | Staff 1 | [5 empty] | Left Fall 2023 | NA
Staff 17 | SC 10 | 42543 | 882 | Mental Health Therapist | MDC Wolfson/Kendall (50 students) | MDC North Care Coord. (15 students) Mental Health (40 students) | 0 | 728 | -882 | 15 | 40 | Approved as a mental health therapist and should not be doing care coordination under that job title. | Pending
Staff 3 | SC 3 | 41957 | 1470 | Program Manager | 50 Citrus/Project UP-START North 50 Homeless community | 50 Citrus/Project UP-START Countywide 20 Homeless community + 50 Support 30 Edison | 61.38 | 0 | -1408.62 | 100 | 30 | Reduced direct care coordiantion hours from last year's contract because staff was unable to meet participants in-person on a monthly basis. Students are countywide and the travel is extensive. | Will keep hours low for next year.
Staff 17 (last day March 22, 2024) | SC 5 | 41961 | 1029 | NA | 50 MDC North 30 transitioning to MDC | 30 students from MDC North assigned, 0 served | 925.5 |  |  |  |  | Staff person was asked to transition roles from something else and did not transition. Last day was March 22, 2024 | NA
Staff 6 | SC 6 | 41918 | 294 | SC 6 | 12 Field Academy | 12 Field Academy | 241.425 | 312 | -52.575 | 12 | 40 | Data has not been entered. | Will move this staff mostly/all off of FNP for next year so she can continue to serve the Field Academy families.
Staff 2 | SC 7 | 41917 | 588 | SC 7 | 12 Field Academy | 12 Field Academy | 866.81 | 156 | 278.81 | 12 | 40 | Data has not been entered. | Will move this staff mostly/all off of FNP for next year so she can continue to serve the Field Academy families.
Staff 5 | SC 9 | 41965 | 588 | SC 9 | 12 Field Academy | 12 Field Academy | 155.625 | 312 | -432.375 | 12 | 40 | Data has not been entered. | Will move this staff mostly/all off of FNP for next year so she can continue to serve the Field Academy families.
Staff 9 | SC 11 | NA | 420.75 | SC 11 | 10 Casa V | 10 Casa V | 578.25 | 52 | 157.5 | 10 | 0 | The residence has been under renovation and has not prioritized data entry. | Continue in same role
Staff 18 | SC 12 | NA | 438.75 | NA | 15 students | Dropped | 0 |  | -438.75 |  |  | Unable to meet i-person once per month
Staff 19 | SC 12 | NA | 438.75 | NA | 15 students | Dropped | 0 |  | -438.75 |  |  | Unable to meet i-person once per month
Staff 20 | Attorney | NA | 514.5 | Attorney | 20 students | Staff 1 and Staff 10 | 0 |  | -514.5 |  |  | Approved to provide legal services, not care coordiantion.
Staff 21 | Staff Lawyer | NA | 771.75 | Staff Lawyer | 30 students | Staff 11 | 0 |  | -771.75 |  |  | Approved to provide legal services, not care coordiantion.
Staff 22 | College Coach | NA | 738.56 | NA | MDC--county-wide (80 students) | Dropped | 0 |  | -738.56 |  |  | Left Spring 2023
Staff 10 | PM/SC 1 | 42551 | 441 | Program Director | The One (50 students) First Star (30 students) | 5 LFCA 30 First Star 50 Support of The One, 50 Support Citrus/Project UP-START 25 MDC | 404.55 | 0 | -36.45 | 35 | 125 | Has spent the past few months planning college tour. | Pending
Staff 4 | SC 1 | 45537 (41915) | 441 | SC 1 | P3 (10 students) Mission Northstar (30 students) | 10 P3 30 Mission Northstar 15 His House 20 The One 30 Support First Star | 660.75 | 289 | 219.75 | 105 | 30 | Brought to fulltime starting Feb 1 2024, and has a very large caseload. Struggeling to manage all contacts, so data entry becomes last priority. | Keep her in this role and continue training her. She lives near North Campus, so would like to keep her there and reallocate some students to New Hire at Educate Tomorrow who will be staffed in MDC North area. New hire planned for summer 2024.
Staff 23 | PM/SC 2 | 42550 | 735 | NA | 50 Citrus/Project UP-START SOUTH 50 Community Partners Support (First Star, LFCA, FFCR) | Most dropped | 0 |  | -735 |  |  | Left early Oct 2022
Staff 4 | Executive Internship Director | 33155 | 0 | Executive Internship Director | NA-only mental health (10 families) | NA-only mental health (10 families) 10 P3 Support | 0 | 260 | 0 | 0 | 20 | Approved as mental health therapist and does not provide care coordination. | Continue in same role
Staff 1 | Program Director | 42661 | 220.5 | Head of Data | LFCA (50 students support) Andrea's students from the South (10 students) Emergency requests | 10 Andrea's students 5 LFCA 50 Emergency requests navigation (short-term support) 50 Intake of new students (short-term support and transition to other staff) 30 LFCA (support) | 431.52 | 0 | 211.02 | 15 |  | A lot of time spent to supporting staff and data entry processes. | Continue in same role
Staff 13 | CBDO | 33152 | 0 | CBDO | NA | Group life skills instruction, active care coordiantion | 810.75 | 0 | 810.75 | 30 |  | Data was not being captured in Trust Central because it wasn't communicated to do so. We will communicate that now. | Continue in same role
-3569.12
Total Direct Service Hrs |  |  | 12004.11 |  |  |  | 7228.94 | 3045
Optional Activities
Indv. Mental Health | [6 empty] | 909
Legal Services | [6 empty] | 624
Group Academics | [6 empty] | 888
Indv. Academics | [6 empty] | 260
Group Life Skills | [6 empty] | 364
Total Optional Activities | [6 empty] | 3045
Note on D15: Amy Rubinson: Lost 2,024 hours here
Note on H27: Amy Rubinson: The contract shows 7228.94 as our direct service hours I realized that this was becuase we had the hours for Virginia under Optional Activities, but in the contract, they are listed as care coordiantion hours.